## Slide 1
KICK-OFF Meeting:
Evaluating how Blockchain can transform the Pharmaceutical and Healthcare industry
06-Sep-2017

## Slide 2
Agenda:
Welcome
Introduction/members
PHUSE Workstream Support
Logistics/meetings- 30min biweekly
Common workspace: PHUSE
Set up sub-work group
Project plan- include reviewers from regulator
and academia perspective
8. Risks
9. Next Steps

## Slide 3: Project members
Co-leads:
  Adama Ibrahim (Biogen)
  Christopher Hart (Manchester Informatics Limited)
  Disa Lee Choun (UCB)
Members:
  Maria Berjegard (AstraZeneca)
  Marcus Bjareland (AstraZeneca)
  Farzad Faramarzi (AstraZeneca)
  Kerstin Forsberg (AstraZeneca)
  Hariprasad Radhakrishnan (AstraZeneca)
  Eric Wu (Gilead)
  Anders Bergkvist (Merck)
  Aji Barot (HealthUnlocked)
  Bert Hartog (Johnson&Johnson)
  Fernand Maes (Johnson&Johnson)
  Zakaria Arrassi (UCB)
  Marc Casals (UCB)
  Ellen Vermaere (UCB)
  Richard Shute
Call for volunteers
Regulatory SME
IT BlockChain SME

## Slide 4: Functional Background - 1
Name | Functional Background | BlockChain Interest | Sub Group Interest Use Case | Sub Group
Adama Ibrahim (Biogen) | Clinical Operations | Site payments, oversight | Any | 3
Christopher Hart (Manchester Informatics Limited) | Biometrics/Informatics | Data integrity & access | Any | 
Disa Lee Choun (UCB) | Clinical Operations | Market drugs/bring drugs quicker to support patients/unmet needs | Any, Clinical, Contract, vendor oversight | Any, 1 or2
Maria Benjegård (AstraZeneca) Kerstin |  |  |  | 
Marcus Bjäreland (AstraZeneca) |  |  |  | 
Farzad Faramarzi (AstraZeneca) | Life science architect, IT, informatics | Clinical data sharing and transparency, security | Standardisation of fingerprint on clinical trial data | 1
Kerstin Forsberg (AstraZeneca) |  |  |  | 
Hariprasad Radhakrishnan (AstraZeneca) | IT, informatics | Supply chain, data security, finance | Any, Supply chain, data security, finance | 
Eric Wu (Gilead) |  |  |  | 

## Slide 5: Functional Background - 2
Name | Functional Background | BlockChain Interest | Sub Group Interest Use Case | Sub Group
Anders Bergkvist (Merck) | Research, protein, molecular biology, bioinformatics | Share trust, autonomy | Any, supply chain | 1 or 3
Aji Barot (HealthUnlocked) | Health economist, health psychology, patient support | Patient acceptability, smart contract | Clinical trial | 1 (lead)
Bert Hartog (Johnson&Johnson) |  |  |  | 
Fernand Maes (Johnson&Johnson) |  |  |  | 
Zakaria Arrassi (UCB) |  |  |  | 
Marc Casals (UCB) | Technology strategy, strategic resourcing | EMR/EHR queries | Any | 
Ellen Vermaere (UCB) |  |  |  | 
Richard Shute | Medicinal Chemistry, informatics/IT | Pre-clinical | Pre-clinical | 3

## Slide 6: Phuse Workstream Support
What Phuse can do for you…
  Update wiki page (own home page as workspace) http://www.phusewiki.org/wiki/index.php?title=Blockchain_Technology
  Meeting organization and minutes
  Documents storage
  White Paper Template

## Slide 7: Logistics
Meeting frequency…
Group Type | MAIN | SUB
Frequency | Biweekly 30 mins | Determined by team
Purpose | Oversee timelines Share updates Review risks Discuss merged all sections | Specific to sections Research Write up Review comments
Organizers | Phuse Project Assistant | 

## Slide 8: Project Scope
Introduce BlockChain and describe how it works
Pre-requisites to adopt BlockChain
Understand the qualities of BlockChain relevant to the Pharma setting and the example of use cases and applications
Provide high level analysis of Pros/Cons of BlockChain in Pharma and Healthcare
Emerging Trends
& Technology
Educating for
the future

## Slide 9: Sub-work group assignments
Group 1. Introduce BlockChain and describe how it works + two use cases
  Sub Group Leader: Aji
Group 2. Pre-requisites to adopt BlockChain: Regulatory/FDA statement, IT and Pharma/Healthcare landscape, “are we ready for blockchain”, + two use cases
  Sub Group Leader:
Group 3. Understand the qualities of BlockChain relevant to the Pharma setting (examples). Provide high level analysis of Pros/Cons of BlockChain in Pharma and Healthcare: two use cases
  Sub Group Leader:
Example Use cases (detailed): TEAM TO AGREE
  Clinical
  Supply Chain

## Slide 10: Project Deliverable and Timelines
Deliverable | Timelines
Provide a white paper that: Includes an overview of BlockChain Analyses the current process and areas where BlockChain would have most impact (i.e. efficiency, change management,…) Proposes Use Cases where Blockchain would transform the current landscape | Researching Blockchain and implementation details: 3 months Finalising the whitepaper: 6-9 months
Communication plan: Publication, presentation, and webinars | Propose presentation DIA in June 2018 PhUSE Conference in June 2018 Others (tbd)

## Slide 11: Project Plan- timelines
Milestone | Timeline
Kick off Meeting | Sept 2017
Sub Group Formation | Sept 2017
Sub Section Headings (Phuse Template) | Oct 2017
Researching and Send Draft for Team Review | Dec 2017
Review Cycle 1 (2 weeks turnaround) | Dec 2017
Sub Group incorporate comments from Review | Jan 2018
Sub Group Share Final Draft for merging of All Sections | Jan 2018
Review Cycle 2 – Final Team Review (2 weeks turnaround) | Feb 2018
Executive Summary | Feb 2018
Final Review – PHUSE/Independent Reviewer | March 2018
Presentation Slides | April 2018

## Slide 12: Sources/Researching
Brainstorming on resources
  Literature
  Vendors
  Conferences
  Other?

## Slide 13
Risk | Trigger | Risk Owner (s) | Mitigation
Team membership changes/commitment (availability) impacting on timelines | Team members missing meetings Or high team turnover | Sub Team Leader | Share contact details Share availability (holidays or work commitments) Plan face to face meetings Make it fun
Another group/company produces a similar white paper (IBM, Deloitte etc) | Publication found online or at conferences | ALL | Maintain a cross industry collaboration Create a white paper that is more authentic Ensure content need to stand out, more detailed, what is the ‘sweet spot’, why is the change necessary
Varied knowledge on Blockchain | Lack of depth in content of sections | ALL | Project Leads to ensure engagement to wider group on linkedin All to consider joining other block chain group and invite people to join the linkedin group All to consider inviting experts/vendors to give talks to a Phuse working group webinar
Risk

## Slide 14: Next Steps..
Update of Kick off Meeting for people not able to join
Update contact details in PhUSE workgroup
Agree on Sub Team members
Team agree Use Cases
Sub Team Leaders reach out to Phuse to coordinate meetings
Cross industry collaboration communication to share internally - Phuse

## Slide 15
Thank you